Yearly Work Programme for APG2012 Working Parties

(as on February 2010)

2010

| Programme Item | By who | By when |
| --- | --- | --- |
| Prepare APT Common View on WRC-12 agenda items or, as necessary, any Common Input to the relevant ITU-R WPs | All members | In preparation for APG2012-3 [8-12 March 2010] |
| Update APG Web Site with Preliminary Views | APT Secretariat | Following APG2012-3 |
| Track ITU-R WP outcomes and other regional and international groups output related to WRC-12 agenda items and forward available information to the APT Secretariat for posting on the relevant WP webpages | Working Party Chairmen/ DG Chairmen | In accordance with ITU-R and other groups’ meeting schedules |
| Develop Common Proposals by correspondence to PP-10 as necessary | All members | In preparation for PP-10 |
| Summary of ITU-R studies, output of other regional groups and international organisations and APT Preliminary Views | WP Chairmen and DG Chairmen | In preparation for APG2012-4 [13-18 December of 2010] |
| Develop Common Proposals on WRC-11 agenda items to CPM11-2 based on available ITU-R studies and other groups’ outputs | All members | At APG2012-4 [13-18 December of 2010] |

2011

| Programme Item | By who | By when |
| --- | --- | --- |
| Update APG Web Site with Common Proposals | APT Secretariat | Following APG2012-4 |
| Track other regional and international groups output related to WRC-12 agenda items and forward available information to the APT Secretariat for posting on the relevant WP websites | WP Chairmen and DG Chairmen | In accordance with ITU-R and other groups’ meeting schedules |
| Summary of ITU-R studies, output of other regional groups and international organisations and APT Preliminary Views/Common Proposals | WP Chairmen and DG Chairmen | In preparation for APG2012-5 [June/July 2011] |
| Develop Common Proposals on WRC-12 agenda items to the WRC based on available ITU-R studies and other groups’ outputs | All members | At APG2012-5 [June/July 2011] |
| Develop Common Proposals on RA-12 agenda items based on available ITU-R studies and other groups’ outputs | All members | At APG2012-5 [June/July 2011] |
| Update APG Web Site with Common Proposals | APT Secretariat | Following APG2012-5 |