|  | ASIA-PACIFIC TELECOMMUNITY |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | The Eleventh South Asian Telecommunications Regulators’ Council (SATRC-11) |  |  | Document SATRC-11/OUT-02 |  |
|  | 24 – 26 November 2009, Colombo, Sri Lanka |  |  | # 26 November 2009 |  |

The way forward: satrc action plan phase iiI

- Objective

The SATRC Action Plan aims at addressing the regulatory issues and challenges of common concern to its members that arise due to market dynamics, technological developments, and innovations in the field of information and communications so as to harness their full potential for the benefit of all by utilizing the expertise and financial resources available from within its member countries. In Action Plan Phase III, the SATRC will cover a wide variety of issues related to the regulators under several working groups. Besides working group activities Action Plan Phase III will implement a number of workshops on relevant topics for capacity building.

- Plan and Estimated Budget for SATRC Action Plan Phase III: Time Frame 2010 – 2011

| Sl. No | Working Group | Methodology | Work Items | Expected Output | Estimated Budget (US$) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Policy and Regulation | Working Group chaired by India and at least one expert from each SATRC Country. One physical meeting per year. Working Group defines the scope of each work item and expected outputs in defined time frame | Adoption of green technologies and safety of wireless networks | SATRC Recommendations Reports Guidelines Opinion papers | 24,000 | One fellowship per administration will be granted for attending Working Group Meeting |
|  |  |  | Facilitation of broadband in SATRC countries |  |  |  |
|  |  |  | CIIP and Cyber security |  |  |  |
|  |  |  | VoIP Issues |  |  |  |
| 2. | Spectrum | Working Group chaired by Islamic Republic of Iran and at least one expert from each SATRC Country. One physical meeting per year. Working Group defines the scope of each work item and expected outputs in defined time frame | Pricing in Spectrum Allocation | SATRC Recommendations Reports, Guidelines, Opinion papers Opinion papers | 24,000 | One fellowship per administration will be granted for attending Working Group Meeting |
|  |  |  | Challenges of future technologies in Spectrum Management |  |  |  |
|  |  |  | Spectrum sharing and trading |  |  |  |
|  |  |  | Cross border coordination for reducing interference |  |  |  |
| 3. | Network and Services | Working Group chaired by Sri Lanka and at least one expert from each SATRC Country. One physical meeting per year. Working Group defines the scope of each work item and expected outputs in defined time frame | Ensuring quality mobile handsets to South Asian Consumers | SATRC Recommendations, Reports, Guidelines, Opinion papers | 24,000 | One fellowship per administration will be granted for attending Working Group Meeting |
|  |  |  | Evolution of NGN and NGA: Interconnection tariffs in SATRC countries |  |  |  |
|  |  |  | Retail tariffs: QoS sensitive pricing for IP based services |  |  |  |
|  |  |  | Roaming and international tariffs |  |  |  |
| 4. | Capacity Building | Three training based workshops will be organized on various topics in order to train the officials from the regulatory bodies. The topics would be related to the activities of the SATRC Working Group activities and recent trends in regulations | - Workshop on Spectrum | Workshop Proceedings | 62,000 | One of the workshops will be funded by Extra Budgetary Contribution by Japan. Pakistan will provide facilities for using the resource available for capacity building. 2 fellowships for each SATRC Administrations will be granted |
|  |  |  | - Workshop on Policy and Regulation |  |  |  |
|  |  |  | - Workshop on Network and Services |  |  |  |
| 5. | SATRC Web Portal | Collection of related information from the SATRC member regulators and make those available of APT Website for information and experience sharing | Developing SATRC Web Portal by APT Secretariat | SATRC Web Portal on APT Website |  | APT Secretariat will develop the web portal by the assistance of Members |
| 6. | Consultant Fee | Consultant will assist the working groups to all aspects and report the overall activities of the Action Plan Phase III |  |  | 20,000 | APT Secretariat will appoint the consultant in consultation with SATRC Chairman |
| 7. | Miscellaneous Expenses |  |  |  | 10,000 |  |
| Expected Expenses for Implementation of Action Plan Phase III |  |  |  |  | 164,000 |  |
| Balance leftover from SATRC Action Plan Phase II Fund |  |  |  |  | 54,000 |  |
| Fund to be Collected for Implementation of Action Plan Phase III |  |  |  |  | 110,000 | To be secured by extra budgetary contribution by SATRC Member Administrations |

Time Frame:

In order to start the SATRC WG activities in a timely manner, it is suggested that:

- Regulators who takes the chairmanship of the Working Group should send the name of the chairman of the Working Group by the end of December 2009

- Regulators should nominate at least one expert for each Working Group. Regulators are requested to send the name of the experts of each Working Groups by the end of December 2009

After the names of the chairmen and experts are received, APT Secretariat will create email reflectors and initiate the WG activities. Consultant for SATRC will also be appointed by APT Secretariat on competitive basis in shortest possible time frame.

3.  Pledge of Extra Budgetary Contribution for Implementation of Action Plan Phase III

| No. | Country | Administration | Pledged Contribution (US$) |
| --- | --- | --- | --- |
| 1 | Afghanistan | Afghanistan Telecom Regulatory Authority (ATRA) | US$ 5,000 |
| 2 | Bangladesh | Bangladesh Telecom Regulatory Commission (BTRC) | US$ 10,000 |
| 3 | Bhutan | Bhutan Information, Communications & Media Authority (BICMA) | US$ 5,000 |
| 4 | India | Telecom Regulatory Authority of India (TRAI) | US$ 40,000 (Subjected to the approval of the Govt.) |
| 5 | Iran | Communications Regulatory Authority (CRA) | US$ 11, 000 (Subjected to the approval of the Govt.) |
| 6 | Maldives | Telecommunications Authority of Maldives (TAM) | US$ 4,173 (Subjected to the approval of the Govt.) |
| 7 | Nepal | Nepal Telecom Authority (NTA) | US$ 5,000 |
| 8 | Pakistan | Pakistan Telecom Authority (PTA) | US$ 15,000 (Subjected to the approval of the Govt.) |
| 9 | Sri Lanka | Telecommunication Regulatory Commission (TRC) | US$ 15,000 |
| 10 | Japan | Support for SATRC Activities through Extra-Budgetary contribution from Japan (EBC-J). | Subject to the confirmation of Japanese Administration, Japan will support a workshop. The details and the amount will be communicated later to the APT secretariat. |
| TOTAL SATRC-EBC FUND |  |  | US$ 110,713.00 |